## UI Tasks - All Version
Feature | Page | Main Tasks | Sub Tasks | Progress | Started Date | Completion (%) | Pending Remarks | Target End Date | End Date | Remarks/ Technical Notes | Lead Note/ Action | Progress List
All Version | All Versions Page | Implement Versions List Grid |  | Partially Done | 2025-04-04 | 70 | Pending Integration with Backend API 1. RetrieveProjectDetails by Project Id, will return Version List, Project Metdata if versions list available else will return Empty Versions List Template 2. Implement Copy Functionality, Backend API integration, when click it will trigger Backend API, then copy the selected Version and return the updated the List 3. Comment Functionality [TBD] | Pending Backend Completion |  |  |  | To Do
|  | Implement Version Detail Card |  | Partially Done | 2025-04-07 | 90 | Pending to details from the Backend API | Pending Backend Completion |  |  |  | In Progress
| Version Details Page [Scheduling] | Implement All Version To Version Details Intermdeiate Transistion Page |  | In Progress | 2025-04-08 |  | This is a common functionality which is used by the other modules also. So implement should be a configurable common comoponent | 2025-04-09 |  |  |  | Done
|  | Implement Navigation to version details page |  | Done | 2025-04-04 |  |  |  | 2025-04-07 |  |  | Hold
|  | Implement Empty State Page and Functionality |  | Done | 2025-04-07 | 100 | This is a common functionality which is used by the other modules also. So implement should be a configurable common comoponent | 2025-04-07 |  |  |  | Partially Done
|  | Implement Scheduling/ Task Grid | Implement custom feature store | Done | 2025-04-01 |  |  |  | 2025-04-02
|  |  | Implement feature header [UI] | Done | 2025-04-02 |  |  |  | 2025-04-03
|  |  | Implement custom form control, as the Grid row to enable user to provide inputs and to capture user inputs. | Done | 2025-04-01 |  |  |  | 2025-04-02 | 1. Should support to handle each Task/ SubTask independently 2. Should be able to inject validations/ errors indepdently
|  |  | Enable Rows To be selectable [Primeng Feature] | Done | 2025-04-01 |  |  |  | 2025-04-01
|  |  | Enable Select All Rows Header Checkbox [Not Primeng Feature], with Intermediate status | Done | 2025-04-03 |  |  |  | 2025-04-03 | * Implemented custom behviro 1. Enable to Select/ Unselect All 2. Enable intermediate select check status when select partially 3. Enable to Select/ Unselect Rows indepdently after Select All First
|  |  | Add Sub Task Row Action | To Do | 2025-04-08 |  |  | 2025-04-09 |  | 1. Support only for the inherited row, not consider selected rows by checkboxes 2. Add Empty Task at the bottom of the subtasks
|  |  | Add Resource Row Action | To Do | 2025-04-09 |  |  | 2025-04-10
|  |  | Add rows | Done | 2025-04-04 | 100 |  |  | 2025-04-07 | 1. Add Empty Row at the bottom of the Task Grid 2. Enable adding Sub Task/ Resources
|  |  | Duplicate Rows | Done | 2025-04-04 | 100 |  |  | 2025-04-07 | 1. Duplicate selected rows [deep clone] 2. Place the duplicate at the bottom of each selection ex: if select multiple parent nodes, then duplicate each row at the bottom of the Task Grid, following the sequence ONLY DUPLICATE PARENT NODES [NOT SUB TASKS]
|  |  | Delete Rows | Done | 2025-04-02 | 100 |  |  | 2025-04-03 | 1. Delete selected tasks/ sub-tasks 2. Update sequence No [To confirm] 3. When confirm delete, does it remove from the BE ? [To Confirm]
|  |  | Move Up Rows | To Do | 2025-04-09 |  |  | 2025-04-11 |  | 1. Move selected task/subtask 1 position up 2. Scenarios to handle -> if the Selected Task is the First Item in the List -> Should support for multiple rows to be moved To write custom alogrithm to manage tree hieararchy [Node-Leaf]
|  |  | Move Down Rows | To Do | 2025-04-09 |  |  | 2025-04-11 |  | 1. Move selected task/subtask 1 position down 2. Scenarios to handle -> if the Selected Task is the Last Item in the List -> Should support for multiple rows to be moved To write custom alogrithm to manage tree hieararchy [Node-Leaf]
|  |  | Gantt Chart Show | To Do | [5 empty] | TBD
|  |  | Advisory Notes | To Do
|  |  | Task Table Funnel Filtering | To Do | [5 empty] | This features is not available in PrimeNg Tree Table.Thus needs to implement custom functionality
|  |  | Save | In Progress | 2025-04-07 |  |  |  |  | 1. Trigger when tries to leave the page [try to add resources] without saving the Task Grid Changes 2. Capture only the dirty records from the main source [#####] and send to the BE for save
|  | Merge To DEV |  | To Do | 2025-04-08 |  |  | 2025-04-08
|  | Resource Page [Modal] |  | To Do | [5 empty] | TBD
Resource Page Modal | Cash Section | Cash Component UI [Pixel Perfect] |  | To Do | 2025-04-10 |  |  | 2025-04-11
|  | Cash Detail Retrieval Func |  | To Do
|  | Cash Detail Save Func |  | To Do
To Do