## UI Tasks - All Version
Feature | Page | Main Tasks | Sub Tasks | Progress | Started Date | End Date | Remarks/ Technical Notes | Lead Note/ Action | Progress List
All Version | All Versions Page | Implement Versions List Grid |  | In Progress | 2025-04-04 |  |  |  | To Do
|  | Implement Version Detail Card |  | To Do |  |  |  |  | In Progress
|  | Implement All Version To Version Details Intermdeiate Transistion Page |  | To Do |  |  |  |  | Done
|  | Implement Navigation to version details page |  | In Progress | 2025-04-04 |  |  |  | Hold
| Version Details Page [Scheduling] | Implement Scheduling/ Task Grid | Implement custom feature store | Done | 2025-04-01 | 2025-04-02
|  |  | Implement feature header [UI] | Done | 2025-04-02 | 2025-04-03
|  |  | Implement custom form control, as the Grid row to enable user to provide inputs and to capture user inputs. | Done | 2025-04-01 | 2025-04-02 | 1. Should support to handle each Task/ SubTask independently 2. Should be able to inject validations/ errors indepdently
|  |  | Enable Rows To be selectable [Primeng Feature] | Done | 2025-04-01 | 2025-04-01
|  |  | Enable Select All Rows Header Checkbox [Not Primeng Feature], with Intermediate status | Done | 2025-04-03 | 2025-04-03 | * Implemented custom behviro 1. Enable to Select/ Unselect All 2. Enable intermediate select check status when select partially 3. Enable to Select/ Unselect Rows indepdently after Select All First
|  |  | Add Sub Task Row Action | To Do |  |  | 1. Support only for the inherited row, not consider selected rows by checkboxes 2. Add Empty Task at the bottom of the subtasks
|  |  | Add Resource Row Action | To Do
|  |  | Add rows | To Do |  |  | 1. Add Empty Row at the bottom of the Task Grid 2. Enable adding Sub Task/ Resources
|  |  | Duplicate Rows | To Do |  |  | 1. Duplicate selected rows [deep clone] 2. Place the duplicate at the bottom of each selection ex: if select multiple parent nodes, then duplicate each row at the bottom of the Task Grid, following the sequence if select Sub Tasks, duplicate the Sub Tasks following the sequence
|  |  | Delete Rows | Done | 2025-04-02 | 2025-04-03 | 1. Delete selected tasks/ sub-tasks 2. Update sequence No [To confirm] 3. When confirm delete, does it remove from the BE ? [To Confirm]
|  |  | Move Up Rows | To Do |  |  | 1. Move selected task/subtask 1 position up 2. Scenarios to handle -> if the Selected Task is the First Item in the List -> Should support for multiple rows to be moved To write custom alogrithm to manage tree hieararchy [Node-Leaf]
|  |  | Move Down Rows | To Do |  |  | 1. Move selected task/subtask 1 position down 2. Scenarios to handle -> if the Selected Task is the Last Item in the List -> Should support for multiple rows to be moved To write custom alogrithm to manage tree hieararchy [Node-Leaf]
|  |  | Gantt Chart Show | To Do |  |  | TBD
|  |  | Advisory Notes | To Do
|  |  | Save | To Do |  |  | 1. Trigger when tries to leave the page [try to add resources] without saving the Task Grid Changes 2. Capture only the dirty records from the main source [#####] and send to the BE for save
|  | Resource Page [Modal] |  | To Do |  |  | TBD